UW-Whitewater

Event Process Timeline and Worksheet

Events that have large numbers of attendees, off-campus guests, alcohol, or are unique in nature should follow the guide of timeline below. UW-W staff determine if these additional requirements are necessary for your event.

- Check on Space Availability

  - For most spaces, contact UC-Room Reservations at 262-472-1175.

  - For athletic spaces, contact Recreation Sports and Facilities at 262-472-1145.

- Tentatively Reserve the Campus Space

  - Spaces will be held for groups who reserve the spaces and follow all necessary steps to use the space (event advising, alcohol use approval, catering, and/or special event regulations, as appropriate).

- Review the Special Event Policy and Create your Timeline Below

  - The full Event Policy can be accessed on the Policy Library

Your Event Date: ________________ (fill in the deadline column below based upon your event date)

| Event Process Timeline and Worksheet |  |  |  |
| --- | --- | --- | --- |
| Time Needed Prior to Event | Details | Communication | Deadline |
| 45 Days Prior | Approval by University Police of any event with 450 or more attendees (requires additional staffing) | PD notified through reservation process |  |
| Around 21 Days Prior | Meeting with Event Advising Staff | Invite sent by Room Reservations; Sponsor select appointment time |  |
| 21 Days Prior | Activity Reservation Form submitted to UC Room Reservations/Building Supervisor, UW-W PD, Sponsor, Student Organization Advisor or Department Head | Final details sent to be confirmed and entered into 25Live |  |
| 14 Days Prior | Police/CSO Staffing needs confirmed with quote for expenses | PD reaches out to Sponsor to confirm and provide quote |  |
| 7 Days Prior | All Sponsors working event complete Online Event Management and Safety Training | PD sends training link to primary sponsor to disseminate |  |
| Day of Event | Attend Pre-Event Meeting - Make Introductions - Assign Staff Locations and Tasks - Review Emergency Procedures - Share Agenda for Event - Share Event Limitations (capacity, alcohol, guests, etc.) - Distribute Nametags/Staff and Sponsor Identification - Share Plan for Attendance Tracking | All individuals working event (including CSOs, UW-W PD, Sponsors, Building Managers, Advisor) |  |
| 14 Days POST Event | Billing completed and sent to sponsor | University Departments (PD, Catering, Facilities, etc.) |  |
| 30 Days POST Billing | Payments completed | Sponsor completes payments |  |